## Slide 1: Prog4Biz/BOTT
Tuesday, June 1st

## Slide 2: Agenda
Introduction | Round-table introductions
BOTT update | Integration for external invoicing
Milestones and deadlines | An overall plan for finishing internal invoicing
Next steps | What happens now?
The purpose of this meeting is to discuss the progress so far and become aligned on what will happen next

## Slide 3: 1. Introduction | Round-table introductions

## Slide 4: 2. BOTT update | Integration for external invoicing

## Slide 5: BOTT update
BookitLab sales order/external invoicing integration
The creation of functional design for external invoicing integration has begun
Conducted two workshops so far
All universities are involved
Topics:
  Fields in invoice
  The different types of sale (instrument, service, prop etc.)
Functional design is estimated to be completed by end of June
 | May |  | June | 
 | 17.05-21.05 | 24.05-28.05 | 31.05 – 04.06 | 07.06-11-06
Kick-off meeting |  |  |  | 
Workshop 1 |  |  |  | 
Workshop 2 |  |  |  | 
Workshop 3 |  |  |  | 
Workshop 4 |  |  |  | 

## Slide 6: Timeline: Sales order/ external invoicing
jun
jul
aug
sep
okt
nov
des
Roll-out to production
Activities
Testing
Development
NTNU
go-live
Holiday for
BOTT-project
Functional design
NTNU will need external invoicing before go-live 01.01.2022
There will be limited time during the fall
We should aim for finishing internal invoicing activities before July in order to start development of external invoicing

## Slide 7: 3. Milestones and deadlines | An overall plan for finishing internal invoicing

## Slide 8: Milestones and suggested deadlines
Data flow | Milestone | Status | Action | Responsible | Suggested deadline
K1 | API is set up and ready to test | Currently in QA and soon ready for testing | Will set up a test session | BOTT-INT | -
 | Prog4Biz unit testing of API |  | To be decided | Prog4Biz | June 9th
 | End to end test of the K1 |  | To be decided | All | Workshop: June 10th
K2 | BookitLab API to get active projects is set up and ready to test | Delivered and awaiting testing |  | Prog4Biz | -
 | BookitLab API to put project data is set up and ready to test | Delivered and awaiting testing |  | Prog4Biz | -
 | Microservice for batch update is set up and ready to test | In peer review | Will set up a meeting with BOTT-INT and Prog4Biz to go through | BOTT-INT | Workshops: June 10th
 | Developers test with synthetic data |  |  | All | 
 | End to end test with realistic data |  |  | All | Workshop: June 17th
K4 | API is set up and ready to test | Delivered and ready for testing |  | BOTT-INT | -
 | Prog4Biz unit testing of API |  | Set up a call if needed | Prog4Biz | TBC
 | End to end test of the K4 |  | To be decided | All | TBC
K5 | Part 1: API for sending batch import status to BookitLab is set up and ready for testing | Part 1: Need an API for sending batch status/error | BOTT-INT have offered to define the API | BOTT-INT/Prog4Biz | TBC
 | Part 2: Set up error message reporting through TopDesk |  |  | BOTT-INT | TBC
 | End to end test of K5 |  |  | BOTT INT/Prog4Biz | TBC

## Slide 9: 4. Next steps | What happens now?

## Slide 10: What happens now?
Next steps
Workshops
  K1 & K2: End-to-end test – June 10th
  K2: End-to-end test – June 17th
K1 & K2:
Prog4Biz - Unit test API for K1
Linn - Send invites to WS
Jo – Contact Ernst regarding K1 testing, and K2 when it is ready
Sindre - set up sub-projects and test environment for K1/K2, and coordinate project API set up for production
K4 & K5
Prog4Biz – provide deadlines for K4 and K5 by June 10th
Action points